## Export Worksheet
BLOCK_ID | TWOD_MAND | TWOD | THREED | WELLS | RP | OTHER | TWOD_MAND_COST | TWOD_COST | THREED_COST | WELLS_COST | RP_COST | OTHER_COST | REMARKS | BLOCK_NAME | YEAR | UPDATEDBY | UPDATEDDATE | STATUS
10 | [5 empty] | Drilling Preparation, G&A costs, G&G Studies, etc. | [5 empty] | 14877238 | a) OC approved WP&Budget for FY2014-15 received from operator on 22.07.2014. b) The proposal is being processed for MCM. c) Exploration activity suspended due to non-availability of Forest land diversion by Govt. of Assam since 28.04.2011. Decision of MOEF is awaited. | AA-ONN-2003/1 | 2014 |  |  | MC REVIEWED
14 |  |  |  | 1 |  | G&G support, G&A cost with main office expenditure, PEL fees and Data storage and digitization |  |  |  | 653587 |  | 316477 | MC reviewed. | AA-ONN-2004/2 | 2014 |  |  | MC REVIEWED
15 |  |  |  | 1 |  | G&G, G&A PEL Fees & Overheds |  |  |  | 1500000 |  | 545083 | MC reviewed. | AA-ONN-2004/3 | 2014 |  |  | MC REVIEWED
17 | [5 empty] | G&G, G&A Cost & Overheds | [5 empty] | 58219 | a) Phase I expired on 20.05.2014, hence operator has submitted BE only for G&G, G&A costs. b)Operator has applied for 3rd extension in Phase I for completing WMP as per clause A-7 of New Extension Policy. The proposal is under evaluation by DGH. | AA-ONN-2004/5 | 2014 |  |  | MC REVIEWED
181 |  |  | 0 | 0 | 0 | G&G support, G&A costs and PEL/License fees | 0 | 0 | 0 | 0 | 0 | 68703.39 | Block is under Disputed Area Belt. MCR for WP & B 2014-15 sent to operator for signature | AA-ONN-2005/1 | 2014 |  |  | MC REVIEWED
460 |  | 150 |  | 2 | 0 | Special Studies, Environmental and safety expenses | 0 | 3092782 | 0 | 36585619 | 0 | 1839077 | Approved at DGH,Wells-2 wells-Drilling of one well and spudding of other well (3500 m each). Reviewed and approved by MC. | AA-ONN-2009/1 | 2014 |  |  | MC REVIEWED
548 |  | 150 | 0 | 2 | 0 | Special Studies, Environmental and safety expenses |  | 3016235 |  | 36585619 |  | 1915624 | Approved at DGH,2 wells-Drilling of one well and spudding of other well (3500 m each). Reviewed and approved by MC | AA-ONN-2009/2 | 2014 |  |  | MC REVIEWED
528 |  |  | 0 | 1 | [5 empty] | 8678053 |  | 2392464 | Include G&G suport, G&A cost PEL Fees. | AA-ONN-2009/3 | 2014 |  |  | MC REVIEWED
529 |  | 201 | 84 | 7 |  | 369 |  | 408268 | 82320 | 1938951 |  | 381178 | 2D(API): 205.8 LKM (Processing) and 246 LKM (Interpretation) 3D(API): 84 Sq Km (Interpretation) ONGC processed. Wells: 1 (one) well of 2000 m against MWP well of 5000 m Other: Geochemical Survey of 369 samples(additional) Budgeted amount break up:2D(API)-Processing(98,784 USD) and Interpretation(209,484 USD) | AA-ONN-2009/4 | 2014 |  |  | MC REVIEWED
564 |  |  | 101 |  |  | Analysis study & Investigation, G&G support, G&A cost with main office expenditure, PEL fees and Data storage and digitization |  |  | 1470862 |  |  | 485884 | MC reviewed. | AA-ONN-2010/3 | 2014 |  |  | MC REVIEWED
414 |  |  | 1644.95 |  |  | G&G, G&A, PEL Fees & Analysis Studies |  |  | 83810 |  |  | 1900481 | MCR for WP & B 2014-15 has been sent to Operator for signature | AN-DWN-2009/1 | 2014 |  |  | MC REVIEWED
426 |  |  | 821.7 |  | 200 | G&G, G&A, PEL |  |  | 83810 |  | 79365 | 2039871 | Total Budget= USD 10,350,905, under examination at DGH.3D interpretation-821.7 SKM RP-AVO:200 SKM. MCR for WP & B 2014-15 has been sent to Operator for signature | AN-DWN-2009/13 | 2014 |  |  | MC REVIEWED
431 |  | 1664 |  |  | 1664 | G&G, G&A, PEL Fees & Analysis Studies |  | 83810 |  |  | 158476 | 1709121 | MCR for WP & B 2014-15 has been sent to Operator for signature | AN-DWN-2009/18 | 2014 |  |  | MC REVIEWED
415 |  |  | 1409.3 |  |  | G&G, G&A, PEL Fees & Analysis Studies |  |  | 83810 |  |  | 1798195 | MCR for WP & B 2014-15 has been sent to Operator for signature | AN-DWN-2009/2 | 2014 |  |  | MC REVIEWED
416 |  |  | 2264.71 | 1 |  | G&G. G&A, PEL |  |  | 83810 | 55017844 |  | 3901741 | MCR for WP & B 2014-15 has been sent to Operator for signature | AN-DWN-2009/3 | 2014 |  |  | MC REVIEWED
418 |  |  |  |  | 342.5 | G&G,Basin modelling,G&A, PEL |  | 83810 |  |  | 32619 | 1707025 | Query has been asked from Operator for quantum of 2D seismic data interpretation, Total Budget= USD 1823453. Sent by circulation. | AN-DWN-2009/5 | 2014 |  |  | MC REVIEWED
33 | [5 empty] | G&G, G&A, PEL fees | 0 | 0 | 0 | 9518000 | 0 | 2385000 | Work programme &Budget will be examined once issues related to the blocks are resolved. | CB-ONN-2003/1 | 2014 | 1451 | 10-07-2014 | NOT APPLICABLE
34 | [12 empty] | Block under development/production. (Producing Field) | CB-ONN-2003/2 | 2014 |  |  | MC REVIEWED
35 | [12 empty] | WP & B submitted on 10.06.2014. Karannagar FDP approved by MC on 31.03.2014 | CB-ONN-2004/1 | 2014 |  |  | MC SCHEDULED
36 |  |  | 0 | 1 | 0 | G&G (24 man months), G&G, PEL and G&A | 0 | 0 | 0 | 1148000 | 0 | 414000 | WP & B submitted on 27.05.2014. MCM scheduled at MOP&NG on 31.07.2014 along with IFDP of VAdatal-1 & Nadiad-1. | CB-ONN-2004/2 | 2014 |  |  | MC SCHEDULED
37 |  |  | 0 | 2 | 0 | G&G, PEL and G&A | 0 | 0 | 195000 | 6504000 | 0 | 355000 | WP & B submitted on 12.06.2014 | CB-ONN-2004/3 | 2014 |  |  | MC SCHEDULED
201 | [5 empty] | G&G Studies for 6 man months | [5 empty] | 67000 | Proposal for Waiver of MWP of 2D seismic data for reprocessing of 718 LKM (717.76 LKM rounded off) due to non availability of old seismic data. clairification to MOP&NG sent on 24.04.2014. Decision awaited. MCR for WP & B 2014-15 has been sent to Operator for signature | CB-ONN-2005/10 | 2014 |  |  | MC REVIEWED
188 | [12 empty] | N.A. PEL not accepted by the operator due to less area. | CB-ONN-2005/11 | 2014 |  |  | NOT APPLICABLE
191 |  |  |  | 2 |  |  | 0 | 0 | 0 | 10071322 | 0 | 78710 | IOC submitted WP&BE for 2014-15 on 28.03.2014 for total USD 10,150,032. Proposal for Extension on account of excusable delay sent to MOP&NG vide letter dated 04.02.2014 for 208 days wef 22.03.2014 to 15.10.2014. Decision awaited. MCR in circulation for signature | CB-ONN-2005/2 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
215 | [5 empty] | G&G, G&A, PEL, PCO | [5 empty] | 196270 | MC reviewed. | CB-ONN-2005/3 | 2014 |  |  | MC REVIEWED
200 | [5 empty] | G&G Studies for 5 man months | [5 empty] | 70000 | MCR for WP & B 2014-15 has been sent to Operator for signature | CB-ONN-2005/4 | 2014 |  |  | MC REVIEWED
177 |  | 350 | 83 |  |  | G&A, PEL, PCO |  | 8060 | 16130 |  |  | 11360 | MC reviewed. | CB-ONN-2005/5 | 2014 |  |  | MC REVIEWED
192 |  |  |  | 2 | [5 empty] | 6743878 |  | 626402 | IOC submitted WP&BE for 2014-15 on 28.03.2014 for total USD 7,370,280. Proposal for Extension on account of excusable delay sent to MOP&NG vide letter dated 12.02.2014 for 374 days wef 31.05.2014 to 08.06.2015. Decision awaited. MCR in circulation for signature. | CB-ONN-2005/7 | 2014 |  |  | MC REVIEWED
214 | [5 empty] | Drillng Preparation/Well planning, G&G, G&A, PEL, PCO | [5 empty] | 506860 | MC reviewed. | CB-ONN-2005/9 | 2014 |  |  | MC REVIEWED
530 |  |  | 33 | 1 |  | Part Pre-drilling EIA + G & G support + G& A cost + PEL fees |  |  | 259 | 1380.95 |  | 413.07 | MCR Reviewed. | CB-ONN-2009/1 | 2014 |  |  | MC REVIEWED
531 |  |  | 68 | 2 |  | Pre-drilling EIA studies , data storage ,G & G support , G& A cost PEL fees |  |  | 158.48 | 3809 |  | 416.23 | MC reviewed. | CB-ONN-2009/2 | 2014 |  |  | MC REVIEWED
533 |  |  |  | 4 |  |  |  |  | 174000 | 3660000 |  |  | Operator has submitted the WP & Budget for FY 2014-15, Under approval. | CB-ONN-2009/4 | 2014 |  |  | MC REVIEWED
534 |  |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 16243696 | 0 | 651643 | MC reviewed. | CB-ONN-2009/5 | 2014 |  |  | MC REVIEWED
536 |  |  |  | 5 |  | Part Predrilling EIA stdies , G & G , G& A cost, PEL fees |  |  |  | 5825.41 |  | 681.3 | MCR Reviewed. | CB-ONN-2009/7 | 2014 |  |  | MC REVIEWED
537 |  |  |  | 11 |  | G&G Support, Rig Movement, G&A Cost, Fixed Assets, PEL/License Fees and Overhead |  |  | 1055000 | 96894343 |  | 108721439 | WP & B for FY 2014-15 have been reviewed by MCR No. 02.2014 on 09.07.2014. : MC Reviewed (Processing, Special processing and Interpretation of 136 SKM of 3D data, Drilling of 11 wells and DST & Production Testing for 13 exploratory wells). | CB-ONN-2009/8 | 2014 |  |  | MC REVIEWED
550 |  | 390 | 100 | 2 | 370 | Geochemical 1564 samples |  | 1068000 | 4618000 |  | 71000 | 1450000 | US$ 6245000 FY 2014-15 (BE) | CB-ONN-2010/1 | 2014 |  |  | MC REVIEWED
560 |  | 10 | 65 |  |  | EIA Studies |  | 22584 | 2677262 | 250196 |  | 493311 | MC reviewed. | CB-ONN-2010/11 | 2014 |  |  | MC REVIEWED
551 |  |  | 49 | 4 | 170 | Interpretation of existing data |  |  |  | 1387000 |  | 1050000 | US$ 2437000 FY 2014-15 (BE),RP-49 (3D),170 (2D) | CB-ONN-2010/5 | 2014 |  |  | MC REVIEWED
552 |  |  | 39 | 4 | 39 | Inversion G&G studies |  |  | 1726000 | 2447000 |  | 347000 | US$ 4520000 FY 2014-15 (BE),RP-39 (3D) | CB-ONN-2010/6 | 2014 |  |  | MC REVIEWED
559 |  |  | 42 | 2 | 10 | [6 empty] | 3990626 | Work programme & budget reviewed by MC. | CB-ONN-2010/8 | 2014 |  |  | MC REVIEWED
553 | 54.68 |  | 109.36 | 2 |  |  |  |  | 5477000 |  |  | 402000 | US$ 5879000 FY 2014-15 (BE) | CB-ONN-2010/9 | 2014 |  |  | MC REVIEWED
41 | [5 empty] | NOT APPLICABLE | [5 empty] | 632000 | Total Budget 632000 US Dollar. Discovery (Aliabet-2,3,4) in Phase I & II. Operator did not enter into Phase - III. Combined DOC of Aliabet 2,3 & 4 submitted by Operator on 04.12.2013. DOC under examination at DGH. 2D(Mandatory)/2D/3D/Wells/RP may be Not Applicable/Not Submitted. MCM to be convene along with DOC on 31.07.2014 | CB-OSN-2003/1 | 2014 |  |  | MC SCHEDULED
42 |  |  | 500 | 5 | 0 |  |  |  | 900000 | 3480000 |  | 770000 | Include G&G suport, G&A cost PEL Fees | CB-OSN-2004/1 | 2014 |  |  | MC REVIEWED
48 | [12 empty] | Phase-I with 1st extension expired on 20.11.2012. Contractor has applied excusable delay due to MOD clearance. Contractor was requested either to submit documentary evidence or pay LD for unfinished work for 1 well. Detail along with documentary evidence are yet to be provided by Operator. JV partners are interested in paying cost of unfinished work. MOP&NG has been informed about the status of block vide letter dated 18.03.2014. M/s ONGC response awaited. | CY-DWN-2004/3 | 2014 |  |  | NOT APPLICABLE
53 |  |  | 0 | 1 | 0 | Well monitoring and Post drill analysis | 0 | 0 | 0 | 483870 | 0 | 201977 | some portion of well NPAC &others include integrated & G&G studies&analysis | CY-ONN-2004/1 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
54 |  |  | 0 | 1 | 0 | well monitoring and post drill analysis | 0 | 0 | 0 | 3135841 | 0 | 1842837 | Others include integrated & G&G studies&analysis. 2014-15 (BE) at DGH level completed. MC to be held at MOPNG. | CY-ONN-2004/2 | 2014 |  |  | MC REVIEWED
179 |  |  |  | 3 |  | Analysis,studies,investigation, G&A cost, Fixed Assets, PEL Fees | 0 | 0 | 0 | 12628362 | 0 | 968647 | Submitted on 20/03/2014, MC reviewed on 13/06/2014. | CY-ONN-2005/1 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
451 |  |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 77282048 | 0 | 4440543 | Budgeted amount of 77282048 USD is for one well. | CY-OSN-2009/2 | 2014 |  |  | MC REVIEWED
61 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Operator sought excusable delay due to MoD clearance. DGH views/comments sent to MOP&NG on 05.03.2014. WP Not Required | CY-PR-DWN-2004/1 | 2014 |  |  | NOT APPLICABLE
64 |  |  |  | 10 |  |  | 0 | 0 | 0 | 1437373 | 0 | 0 | Total BE for FY 2014-15 is USD 1633376,Wells-10 core holes. Termination by MOPNG, notice issued on default of BG. | DS-ONN-2004/1 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
432 |  |  | 0 | 2 | 0 | Analysis, studies | 0 | 0 | 12028 | 26524259 |  | 1729037 | Include G&G suport, G&A cost PEL Fees. MOP&NG vide letter dated 10.12.2012 has approved 415 LKM 2D OBC in lieu of balance 2D and 3D seismic. Wells-2 (1 firm + 1 to mature) | GK-OSN-2009/1 | 2014 |  |  | MC REVIEWED
433 |  |  | 0 | 2 |  | Analysis, studies |  |  | 12312 | 13167973 |  | 1103178 | Include G&G suport, G&A cost PEL Fees. MOP&NG vide letter dated 10.12.2012 has approved 440 LKM 2D OBC in lieu of balance 2D and 3D seismic. Wells-2 (1 firm + 1 to mature) | GK-OSN-2009/2 | 2014 |  |  | MC REVIEWED
549 |  |  | 1361 | 6 |  |  |  |  | 9305545 |  |  | 9197445 | US$10185100 FY 2014-15 (BE) | GK-OSN-2010/1 | 2014 |  |  | MC REVIEWED
561 |  |  | 1625 | 6 |  |  |  |  | 13092805 |  |  | 1040353 | US$14133158 FY 2014-15 (BE) | GK-OSN-2010/2 | 2014 |  |  | MC REVIEWED
76 |  |  |  | 1 | 0 | G&G, G&A, PEL Fees, etc | 0 | 4619 | 462845 | 25080741 | 0 | 1781202 | 1 well under drilling,2D/3D-interpretation stage MCM scheduled at MOP&NG on 06.08.2014 | GS-OSN-2004/1 | 2014 | 126871 | 21-07-2014 | MC SCHEDULED
84 |  |  | 1000 | 2 |  | Structure Modelling Geopressure studies, G&G, G&A, Special studies | 0 | 0 | 830000 | 40958000 | 0 | 4065000 | WP & Budget submitted on 30.12.2013. WP & B for FY 2014-15 consists Drilling of 2 wells. WP & Budget has been reviewed by DGH. MC meeting held on 09/07/2014. WP&Budget approved by MC on 09/07/2014. | KG-DWN-2003/1 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
97 | [12 empty] | MOP&NG is to approve Operatorship to ONGC. | KG-ONN-2003/1 | 2014 |  |  | NOT APPLICABLE
98 | 50 |  | 100 | 4 |  | 200 sub surface core, G&G personnel, G&A cost, Main office expenditure and PEL fees | 820141 |  | 223256 | 61422350 |  | 5842200 | MC reviewed. *1st well spudded on 16.04.2014. Depth of well as on 30.06.2014 is 2455m. Drilling is continued. | KG-ONN-2004/1 | 2014 |  |  | MC REVIEWED
103 |  |  |  | 3 | 0 | G&G, G&A, PEL Fees, etc | 0 | 0 | 1546380 | 76574689 | 0 | 5063391 | ECS has granted extension of exploration period from 06/01/2013 to 30/04/2015. ONGC vide letter dated 06/01/2014 submitted that consequent to grant of extension of exploration contractor is now revsing the WP&Budget estimate for the period of extension and requests to MC to postpone the review of earlier budget. MC scheduled on 06.08.2014 | KG-OSN-2004/1 | 2014 |  |  | MC SCHEDULED
182 | [5 empty] | Block put up in "NO GO Area" | 0 | 0 | 0 | 0 | 0 | 0 | Block put up in "NO GO Area" by MOD | KG-OSN-2005/1 | 2014 |  |  | NOT APPLICABLE
205 | [5 empty] | Block put up in "NO GO Area" | 0 | 0 | 0 | 0 | 0 | 0 | Block put up in "NO GO Area" by MOD | KG-OSN-2005/2 | 2014 |  |  | NOT APPLICABLE
453 |  |  | 30 | 1 |  |  |  |  | 2074524 |  |  | 1947083 | Total BE (Firm) is 4021607 USD Total BE (To Mature) is 35001883 USD which include To Mature drilling Budget of 32623065. Operator requested for excusable delay due to MoD clearance & Legal issue. The same is forwarded to MoPNG vide DGH letter dated 01.07.2014. | KG-OSN-2009/1 | 2014 |  |  | MC REVIEWED
454 |  |  | 40 | 2 |  |  |  |  | 2695032 |  |  | 1977605 | Total BE (Firm) is 4672637 USD Total BE (To Mature) is 56898362 USD which include To Mature drilling Budget of 53156466. Operator requested for excusable delay due to MoD clearance & Legal issue. Clarification sought from Operator for excusable delays. The same is forwarded to MoPNG vide DGH letter dated 01.07.2014. | KG-OSN-2009/2 | 2014 |  |  | MC REVIEWED
455 |  | 4557 | 1288 |  |  | Special Studies, Environmental and safety expenses |  | 27000000 | 2432032 |  | 625000 | 25176121 | Approved. Budget also include the budget of To mature category. 2D Reprocessing of existing data. | KG-OSN-2009/3 | 2014 |  |  | MC REVIEWED
456 |  |  |  |  | 423 |  |  |  | 35500 |  | 279300 |  | Operator requested for excusable delay due to MoD clearance. DGH vide letter dated 20.01.2014 has recommended excusable delay to MOPNG for 510 days on account of MOD clearance. Operator has also submitted proposal for reduction of MWP due to No Go Area and High Risk Area, identified in the block by MOD. DGH vide letter dated 10.06.2014 forwarded proposal to MOPNG. Operator has submitted the WP & Budget for FY 2014-15, Approved by MC. | KG-OSN-2009/4 | 2014 |  |  | MC REVIEWED
408 |  | 2000 | 500 |  |  | Additional WP - 2D seismic Processing Special Studies, Environmental and safety expenses |  | 10463030 | 1154499 |  |  | 6107216 | Approved. | MB-DWN-2009/1 | 2014 |  |  | MC REVIEWED
556 | 630 | 1370 |  |  |  | Integrated Seismic, Magnetic & Gravity data Interpretation 2D(Mandatory)-Interpretation of 630 LKM | 2076238 |  | 0 | 0 | 0 | 200000 | 2D Interpretation of 1370 LKM | MB-DWN-2010/1 | 2014 |  |  | MC REVIEWED
213 |  |  |  | 2 | 0 | G&G & Generation of Locations | 0 | 0 | 0 | 15711263 | 0 | 71260 | Budget for appraisal WP yet to be submitted. MCR has been approved but yet to be signed. MC reviewed the appraisal WP&Budget on 22.07.2014. | MB-OSN-2005/1 | 2014 |  |  | MC REVIEWED
184 | [12 empty] | N.A. Request for special dispensation. ECS Issue, CUMWP is to be collected to regularize the block | MB-OSN-2005/2 | 2014 |  |  | NOT APPLICABLE
178 | [5 empty] | Data Cpopying, Storage etc. G&G Support G&A Cost PEL Fees Parent Company Overheads | [5 empty] | 337217 | MC Reviewed. | MB-OSN-2005/3 | 2014 |  |  | MC REVIEWED
202 |  |  |  | 0 | 0 | G&A, G&G, PEL Fees | 0 | 0 | 95444 | 0 | 0 | 847447 | MWP of Phase-I is completed within 2nd extension. Operator is considering for relinquishment of the block without entering into Phase-II vide letter dated 08.05.2014. The WP&Budget for F.Y. 2014-15 has been examined and reviewed at DGH. MCR sent to operator for signature. | MB-OSN-2005/5 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
203 |  |  |  | 1 | 0 | G&A, G&G, PEL Fees | 0 | 0 | 95444 | 8931819 | 0 | 1265291 | MWP of Phase-I is completed within 2nd extension. Operator is considering for relinquishment of the block without entering into Phase-II vide letter dated 08.05.2014.3D is in interpretation stage. WP&Budget for FY 2014-15 is examined and agreed at DGH. MCR sent to operator for signature. | MB-OSN-2005/6 | 2014 |  |  | MC REVIEWED
555 |  | 4200 | 1000 | 1 |  | G&G suport, G&A Cost, Main Office Expences, PEL Fee. | 0 |  | 4950000 | 130169.02 | 0 | 676807.05 | MC reviewed. | MB-OSN-2010/2 | 2014 |  |  | MC REVIEWED
145 |  |  | 160 | 5 |  | G&G support, G&A cost with main office expenditure, PEL fees and Data storage and digitization |  |  | 3168268 | 28230862 |  | 3205690 | MC reviewed. *1st well spudded on 06.07.2014. | MZ-ONN-2004/1 | 2014 |  |  | MC REVIEWED
206 | [5 empty] | Study of Geologiocal Samples, PDA of Ladmi-I, Data reproduction, Storage, Digitisation, G&G, G&A, PEL | 0 | 0 | 0 | 0 | 0 | 1631192 | Total BE 1631192 USD | PA-ONN-2005/1 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
207 |  |  |  | 1 |  | Analysis, Studies & Investigation, Data Copying, Storage, G&G support, G&A, PEL |  |  |  | 3154375 |  | 2041098 | Total BE (Firm) is 5195473 USD Total BE (To Mature) is 1593289 USD which include To Mature drilling Budget of 1593289 USD | PA-ONN-2005/2 | 2014 |  |  | MC REVIEWED
183 |  |  |  | 1 |  | Special studies, G&G support, G&A and PEL |  |  | 33000 | 3702184 |  | 1984141 | Total BE 5719325 USD.3D is in Interpretation stage | PR-ONN-2005/1 | 2014 |  |  | MC REVIEWED
156 | [5 empty] | G&G support for drilling preparation | 0 | 0 | 0 | 1000000 | 0 | 1483131 | WP&B submitted with OCR on 28.05.2014. DGH Reviewed MCR sent to the operator for signature. | PR-OSN-2004/1 | 2014 | 105389 | 22-07-2014 | MC REVIEWED
163 |  |  | 0 | 3 | 0 | G&G suport, G&A cost and PEL Fees |  |  |  | 1420000 |  | 650000 | Review completed. MCR under circulation. | RJ-ONN-2003/2 | 2014 |  |  | MC REVIEWED
165 |  |  |  | 3 |  | PEL Fees, Geochem. Biostratigraphic analysis & G&G review (Appraisal), G&G & G&A charges |  |  |  | 7409623 |  | 1080613 | Block is in Phase-II and Appraisal period of Punam-1 discovery has expired on 16.06.2014.Operator has submitted Geological note on DOC on 13.06.2014, which is under examination. WP&B is under examination. MC not reviewed yet.Wells-3 (1 MWP, 1 Additional & 1 Appraisal). DGH reviewed. Physical MC meeting scheduled for 28 July 2014 is rescheduled to 7th August 2014 by MOPNG. | RJ-ONN-2004/2 | 2014 |  |  | MC SCHEDULED
185 |  |  |  | 2 |  | G & G Support, General & Administrative Costs, PEL/ License Fee & Affiliate Cost |  |  | 200000 | 12934454 |  | 1385380 | WP & B for FY 2014-15 have been reviewed by MCR No. 03/2014 on 09.07.2014. Third Party 3D Interpretation as part of Project Management and Interpretation, Drilling of Two Exploratory Wells of Depth 2500m and 3000m respectively, Well testing budget will be submitted separately in case of Hydrocarbon indications while drilling the exploratory wells. | RJ-ONN-2005/1 | 2014 |  |  | MC REVIEWED
186 |  |  | 1491 | 3 |  | PEL Fees, Airo magnetic Survey API (7200 stations), HR 3D Interpretation (108 SKM), Pre-SDM (300 SKM, 3D AVO (300 SKM), Pre-Stack inversion (150 SKM), G&G Charges, G&A charges, EIA Study | 0 | 0 | 911088 | 6663109 | 0 | 1843048 | Block in Phase-I. Pre-SDM (300 SKM), 3D AVO (300 SKM), Pre-Stack inversion (150 SKM) is substitute work proposed by operator in lieu of Mandatory 2D API and same will be reviewed after MOPNG approval. A letter is to sent to MOPNG for its view on substitute work. 3D Interpretation-1491 SKM.Wells-3 (1 firm and 2 To Mature Category). DGH reviewed MCR is in circulation. | RJ-ONN-2005/2 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
204 |  |  |  | 2 |  | G&G Support, Analysis, studies, investigation, PEL Fees, G&A cost | 0 | 0 | 0 | 9832060 | 0 | 1027210 | Submitted on 07/04/2014,MC reviewed on 27/06/2014 (by circulation) | RJ-ONN-2005/3 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
167 |  |  |  | 1 |  | G & A Rewa Project Base,G & A,Misc Fixed Assets |  |  |  | 3358113.174 |  | 524308.4 | MC Reviewed. | SR-ONN-2004/1 | 2014 |  |  | MC REVIEWED
172 |  | 400 | 106.7 |  | 300 | G & G Support,General and Administrative cost,PEL Fees |  | 3820000 | 20000 | 282500 | 60000 | 1397200 | The WP for FY 2014-15 comprising of 2D Seismic API ,3D Seismic Interpretation and Re processing is an additional activity beyond MWP of Phase-II. 2D Sesimic Acquisition-400 LKM ,Processing 200LKM and Interpretation 200 LKM,2D Sesimic Re Interpretation 800 LKM.3D Seismic Re Interpretation 106.7 SKM. Wells-Drilling Preparation. 2 D Sesimic Reprocessing(RP)-300 LKM | VN-ONN-2004/1 | 2014 |  |  | MC REVIEWED
173 |  | 200 | 212.4 |  | 200 | G & G Support,General and Administrative cost,PEL Fees | 0 | 1940000 | 20000 | 282500 | 40000 | 975000 | The WP for FY 2014-15 comprising of 2D Seismic API ,3D Seismic Interpretation and Re processing is an additional activity beyond MWP of Phase-II . 2D Sesimic Acquisition-200 LKM ,Processing 100LKM and Interpretation 100 LKM,2D Sesimic Re Interpretation 500 LKM.3D Seismic Re Interpretation 212.4 SKM. Wells-Drilling Preparation. 2 D Sesimic Reprocessing(RP)-200 LKM | VN-ONN-2004/2 | 2014 | 126871 | 21-07-2014 | MC REVIEWED
467 |  | 800 |  | 1 |  |  |  | 160000 |  | 282500 |  | 445500 | Include G&G suport, G&A cost PEL Fees.Wells-1(Pre drilling Act) | VN-ONN-2009/3 | 2014 |  |  | MC REVIEWED
208 |  |  | 275 | 1 | 0 | G&G,G&A,PEL Fee | 0 | 0 | 134095 | 4405120 | 0 | 2183447 | Including drilling preperation $ 712437,3D interpretation-275. WP&B 2014-15 Mc reviewed | WB-ONN-2005/2 | 2014 |  |  | MC REVIEWED
209 |  |  | 0 | 1 | 0 | G&G,G&A,PEL Fee | 0 | 0 | 0 | 6423655 | 0 | 2037987 | Revised/modified WP&B 2014-15 reviewed by MC. | WB-ONN-2005/3 | 2014 |  |  | MC REVIEWED
211 |  |  | 316 | 2 | 0 | G&G,G&A,PEL Fee | 0 | 0 | 134095 | 13533761 | 0 | 2546813 | Including 'To Mature' $ 2361182. WP&Budget 2014-15 MC reviewed. | WB-ONN-2005/4 | 2014 | 126871 | 21-07-2014 | MC REVIEWED

## SQL
select * from psc_wpbudget order by block_name